## Slide 1: Plans and Process for Taking Measurements
Jing

## Slide 2: Measurement Process
Site survey
Pre-requisite
Document site information
On-site measurement taking
Post-requisite
Notes: Minor edits. Stretch “outside” and “other voluntary” for non-binding WG activities with openness and fairness.

## Slide 3: Site Survey
Do a site survey with the person in charge. Record the following information if possible :
Duty and off days
Possible active sources, interferences, and wireless protocol used
Layout or pictures of the site
Type of material of the site
Decide Suitable measuring time and decide possible place to place the antenna

## Slide 4: Pre-requisites
Decide the location of the measurements
Decide the measurements frequency bands, duration, time, etc.
Decide and prepare the measurement setups (how the antenna and devices placed, direction, blockage, etc)
Document all the information (see following slides)
List of all equipment to bring

## Slide 5
This could be done at both site survey and actual site visit and measuring. Information includes :
Description of campaign
Description of measurement site/location
  Measure the dim of the environment and from antenna to sources (both inside and outside)
  Drawing of the measurement site if available (Layout, CAD drawing or PPT). Record location showing all major obstructions/objects, locations of possible RF emitters/active sources inside and outside of the site.
  Type of materials at the site
  Estimate of people working, numbers, etc.
  Kinds of devices and protocols allowed by policy at the site
  Aware of personal apparatus possible as sources (cell phones, radio, RFID, etc)
  Numbers and types of computers, wireless machines, and controllers in use or active
  List and location of APs
Documented Site Information (1)

## Slide 6
Description of device settings
  Location of the measurement antenna
  Pictures of the apparatus settings and measurement site at each measurement location (show the environment around the meas. antenna)
  Description of measurement apparatus : Antenna, Equipment/SA, any attenuators used
Description of measurement settings
  Meta data from the program
    Sampling Rate (M/s)
    Sweep option
    Min Center frequency (MHz)
    Max Center frequency (MHz)
    Filter Bandwidth (MHz)
    Total channels sweeping during capturing
    Threshold (dBm)
    Reference level (dBm)
    Total collection duration (min)
    Buffer duration/min event size (us)
    Frequency dwell time (ms)
  Other could be in the comment field
Documented Site Information (2)

## Slide 7: Procedures of Taking Measurement On Site
Determine a process to observe a big picture :
  Use spike for larger span(~100+MHz depending on need) with Max hold on interested frequency band (900M, 2.4G, 3.5G, 5G, )
Plan for the detail settings for later tool measurement based on big picture
Start measuring, store the outcome(program output and spike output), and for later process

## Slide 8: Post Requisites
Examine the data to see if refinement need to be done for above procedures

## Slide 9: To Do List
Refined code based on need
  More sweep options
  probability p if occupancy rate is over x (currently using 30% & 0.7)
Uncertainty analysis
Threshold offset value